## OPD
OPD (G+3) | Target Date
Brickwork (Shaft Only) | 2026-10-10 | FLOOR | TARGET DATE
Plastering | 2026-10-26 | GF | 2026-10-15
Doors & Windows | 2026-11-15 | FF | 2026-11-20
Flooring & Cladding | 2026-11-25 | SF | 2026-12-10
False Ceiling | 2026-12-10 | TF | 2026-12-25
Toilets | 2026-12-18
Lift works | 2026-11-30
External Finishes | 2026-12-15
Interior works & SS Handrail | 2026-12-24
Power ON | 2026-12-05
HVAC Works | 2026-12-15

## OPD BACKUP
OPD BUILDING
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | UOM | Scope | Achieved till 20th Sep. | Achieved as on 29'sep | Achieved as on 3rd Oct | Balance | Asking Rate | No. of workmen Needed | No. of workmen available
[12 empty] | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure | [6 empty] | 100%
Finishes
Brickwork | 2025-09-10 | 2026-10-10 | cum | 4151 | 3943.45 | 97% | 97.3% | 112.077 | 37.359 | 37 | 18
Internal Plaster | 2025-11-30 | 2026-10-25 | sqm | 50950 | 48402.5 | 96% | 96.5% | 1783.25 | 99.0694 | 10 | 7
Joineries | 2026-01-25 | 2026-11-15 | No. | 717 | 316 | 59% | 61% | 279.63 | 7.17 | 2 | 5
Fire door frame & shutter | 2026-03-21 | 2026-10-30 |  |  | 0 | #REF! |  | 0 | 0
Flooring & Dado | 2025-12-18 | 2026-11-25 | sqm | 29200 | 21900 | 78% | 79.2% | 6073.6 | 123.951 | 41 | 30
False Ceiling | 2026-07-08 | 2026-12-10 | sqm | 15240 | 762 | 28% | 29% | 10820.4 | 169.0688 | 14 | 14
a) Ground Floor | 2026-07-08 | 2026-10-15 |  |  | 0 | #REF! |  | 0 | 0
b) First Floor | 2026-08-02 | 2026-10-28 |  |  | 0 | #REF! |  | 0 | 0
c) Second Floor | 2026-08-27 | 2026-11-20 |  |  | 0 | #REF! |  | 0 | 0
d) Third Floor | 2026-09-21 | 2026-12-15 |  |  | 0 | #REF! |  | 0 | 0
Lift facia granite | 2026-09-30 | 2026-11-25 | sqm | 240 | 0 | 4% | 4% | 230.4 | 4.702 | 1 | 0
Interior Works | 2026-10-25 | 2026-12-24 | sqm | 640 | 0 | #REF! | 0% | 640 | 10.6667 | 1 | 0
SS Handrail | 2026-11-15 | 2026-12-24 | Rm | 475 | 0 | #REF! | 0% | 475 | 12.1795 | 1 | 0
External
Elevation A | 2026-04-04 | 2026-11-15 | sqm | 934.8634 | 541.25 | 54% | 54.2% | 428.1674 | 10.9787 | 3 | 2
Brickwork |  | 0.25 | sqm | 804.8696 | 805 | 97% |  | 804.8696 | -0.017383
Plaster |  | 0.25 | sqm | 1615 | 1360 | #N/A |  | 1615 | -0.03488
MS framing |  | 0.1 | sqm | 345 | 0 | #N/A |  | 345 | -0.0074511
Stone Cladding |  | 0.1 | sqm | 345 | 0 | #N/A |  | 345 | -0.0074511
Glazing |  | 0.2 | sqm | 669.48 | 0 | #N/A |  | 669.48 | -0.014459
Paint |  | 0.1 | sqm | 1270 | 0 | #N/A |  | 1270 | -0.027429
Elevation B | 2026-06-18 | 2026-11-25 | sqm | 447.4736 | 258.3696 | 53% | 56% | 196.8884 | 4.0181 | 1 | 3
Brickwork |  | 0.25 | sqm | 443.4783 | 443.4783 | 97% |  | 443.4783 | -0.009578
Plaster |  | 0.25 | sqm | 780 | 590 | #N/A |  | 780 | -0.016846
MS framing |  | 0.1 | sqm | 215 | 0 | #N/A |  | 215 | -0.0046434
Stone Cladding |  | 0.1 | sqm | 215 | 0 | #N/A |  | 215 | -0.0046434
Glazing |  | 0.2 | sqm | 275.52 | 0 | #N/A |  | 275.52 | -0.0059505
Paint |  | 0.1 | sqm | 435 | 0 | #N/A |  | 435 | -0.0093949
Elevation C | 2026-08-10 | 2026-12-05 | sqm | 564 | 180 | 33% | 34% | 372.24 | 6.3092 | 2 | 2
Brickwork |  | 0.25 |  |  |  | 97% |  | 0 | 0
Plaster |  | 0.25 |  |  |  | #N/A |  | 0 | 0
MS framing |  | 0.1 |  |  |  | #N/A |  | 0 | 0
Stone Cladding |  | 0.1 |  |  |  | #N/A |  | 0 | 0
Glazing |  | 0.2 |  |  |  | #N/A |  | 0 | 0
Paint |  | 0.1 |  |  |  | #N/A |  | 0 | 0
Elevation D | 2026-08-25 | 2026-12-15 | sqm | 431 | 106 | 25% | 25% | 323.25 | 4.6848 | 1 | 0
Elevation A | #REF! | 2026-10-20 |  |  |  | 54%
Elevation B | #REF! | 2026-11-05 |  |  |  | 53%
Elevation C | #REF! | 2026-11-22 |  |  |  | 33%
Elevation D | #REF! | 2026-12-05 |  |  |  | 25%
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-03-12 | 2026-10-20 | Rm | 1500 | 1335 | 83% | 95% | 75 | 5.7692 | 1 | 2
CI/Gi Piping | 2026-01-28 | 2026-10-31 | Rm | 13030 | 10356 | 88% | 89% | 1433.3 | 59.7208 | 5 | 4
Ducting & Insulation | 2025-12-11 | 2026-10-27 | sqm | 7203 | 6780 | 89% | 94.13% | 423 | 21.15 | 2 | 4
Fire Piping installation | 2026-01-10 | 2026-10-25 | sqm | 9363 | 8504 | 91% | 90.83% | 859 | 47.7222 | 4 | 6
MGPS Copper Piping | 2026-09-10 | 2026-11-25 | Rm | 5158 | 0 | 23% | 24% | 3920.08 | 80.0016 | 9 | 0
PTTS Pipe installation | 2026-09-10 | 2026-11-15 | Rm | 630 | 215 | 18% | 34.13% | 415 | 10.641 | 1 | 2
Under deck Insulation | 2026-09-30 | 2026-10-28 | sqm | 3426 | 0 | #REF! | 10% | 3083.4 | 146.8286 | 15 | 6
Second Fix
Wiring | 2026-08-18 | 2026-11-20 | Rm | 46027 | 22092.96 | 45% | 48% | 23934.04 | 543.9555 | 22 | 16
Cable Laying & Panel Instt. | 2026-07-10 | 2026-11-28 | Rm | 16308 | 8643.24 | 51% | 53% | 7664.76 | 147.3992 | 6 | 4
UPS Installation | 2026-10-05 | 2026-10-31 | No. | 4 | 3.6 | #REF! | 90% | 0.4 | 0.016667 | 0 | 0
Dropper Installation | 2026-10-18 | 2026-12-10 | No. | 1517 | 0 | #REF! | 0% | 1517 | 28.6226 | 2 | 0
HVAC Pipe Testing | 2026-08-10 | 2026-11-10 | Rm | 2800 | 2585 | 84% | 92.32% | 215 | 6.3235 | 2 | 0
AHU Connection | 2026-08-19 | 2026-11-28 | No. | 45 | 39 | 48% | 86.67% | 6 | 0.11538 | - | 4
Wet Riser & FHC installation | 2026-08-10 | 2026-10-24 |  |  |  | #REF! | #DIV/0! | #DIV/0! | #DIV/0!
CAT 6 cabling | 2026-08-10 | 2026-11-15 | Rm | 65000 | 16450 | 44% | 44% | 36400 | 933.3333 | 16 | 8
PA & FAS cabling | 2026-07-18 | 2026-11-15 | Rm | 24107 | 18628 | 57% | 77.27% | 5479 | 140.4872 | 2 | 4
Fire Panel Installation | 2026-09-29 | 2026-10-15 | No. | 1 | 0 | #REF! | 0% | 1 | 0.125 | - | 0
Network Switch | 2026-09-29 | 2026-11-20 | No. | 12 | 4 | #REF! | 33.33% | 8 | 0.18182 | 1 | 4
Final Fixture | 2026-11-20 | 2026-12-20 | lot | 1 | 0.02 | #REF! | 2% | 98%
Terrace
PHE Piping installation | 2026-10-10 | 2026-11-15 | rm | 2250 | 0 | #REF! | 0% | 2250 | 62.5 | 6 | 7
Solar Panel Installation | 2026-11-05 | 2026-12-10 | No. | 128 | 0 | #REF! | 0% | 128 | 3.6571 | - | 0
Over Head Tank | 2026-08-22 | 2026-11-25 | No. | 1 | 0.35 | 44% | 60% | 265 | 5.4082 | 3 | 0
Terrace Waterproofing | 2026-08-05 | 2026-12-05 | sqm | 3528 | 3528 | 78% | 100% | 731 | 12.3898 | 2 | 2
Truss with Polycarbonate Sheet | 2026-09-30 | 2026-10-31 | sqm | 1015 | 609 | 60% | 65% | 355.25 | 14.8021 | 3 | 2
Lift Installation with slow speed |  |  | No. | 7 | 4 |  |  | 2.45
2 No.s | 2026-06-05 | 2026-07-30 | No. | 2 | 2 | 100% | 100% | 0 | 0% | - | 0
3 No.s | 2026-08-08 | 2026-10-25 | No. | 3 | 2 | 72% | 85% | 0.45 | 2.5% | 4 | 4
1 No. | 2026-10-11 | 2026-11-28 | No. | 1 | 0 | #REF! | 0% | 1 | 2.083% | 2 | 2
1 No. | 2026-11-15 | 2026-12-10 | No. | 1 | 0 | #REF! | 0% | 1 | 4% | - | 0
Permanent Power
ESS1 to OPD Cable Laying | 2026-09-29 | 2026-10-20 |  |  |  | #REF!
Main LT Panel Energisation | 2026-10-31 | 2026-11-20 |  |  |  | #REF!
Rising Main | 2026-10-28 | 2026-11-25 |  |  |  | #REF!
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
Formulas:
Asking Rate = [Balance]/([TARGET DATE]-(IF([PLAN / ACTUAL START]>TODAY(),[PLAN / ACTUAL START],TODAY())))
TARGET DATE = VLOOKUP([ACTIVITY],[4]OPD!$B1:D111,3,FALSE)
PLAN / ACTUAL START = MIN([PLAN / ACTUAL START, row below]:B15)
PLAN / ACTUAL START = [PLAN / ACTUAL START, row above]+25

## EMR
EMR (G+3) | Target Date
Brickwork | 2026-10-25
Plastering | 2026-11-20 | FLOOR | TARGET DATE
Doors & Windows | 2026-11-20 | GF | 2026-10-28
Flooring & Cladding | 2026-11-30 | FF | 2026-11-25
False Ceiling | 2026-12-18 | SF | 2026-12-18
Toilets | 2026-12-28 | TF | 2026-12-25
Lift Works | 2026-12-26
External Finishes | 2026-12-11
Interior works & SS Handrail | 2026-12-24
CSSD | 2026-11-15
Power ON | 2026-12-12
HVAC Works | 2026-12-21
OT Works / ICU | 2026-12-24

## EMR BACKUP
EMERGENCY BUILDING
2026-10-03
ACTIVITY | PLAN / ACTUAL START | Target Date | UOM | SCOPE | Achieved | Achieved as on 29-sep | Achieved as on 3-Oct | Balance as on 3-oct | Asking Rate | Manpower Needed | Manpower Available
[12 empty] | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure
Finishes
Brickwork | 2025-10-08 | 2026-10-25 | CUM | 4228 | 4092.704 | 96% | 96.8% | 135.296 | 7.5164 | 8 | 8
Internal Plaster | 2026-01-10 | 2026-11-10 | sqm | 55280 | 44224 | 78% | 80% | 11056 | 325.1765 | 27 | 30
Joineries | 2026-03-21 | 2026-12-15 | No. | 782 | 445.74 | 57% | 57% | 336.26 | 4.8733 | 2 | 0
Fire door frame & shutter | 2026-03-21 | 2026-12-15 |  |  | 0 | 0% |  | 0 | 0
Flooring & Dado | 2026-02-20 | 2026-11-30 | sqm | 26142 | 21175.02 | 79% | 81% | 4966.98 | 91.9811 | 9 | 12
False Ceiling | 2026-10-20 | 2026-12-22 | sqm | 11273 | 0 | 0% | 0% | 11273 | 178.9365 | 18 | 0
a) Ground Floor | 2026-07-08 | #N/A |  |  | 0 | #N/A |  | 0 | #N/A
b) First Floor | 2026-08-02 | #N/A |  |  | 0 | #N/A |  | 0 | #N/A
c) Second Floor | 2026-08-27 | #N/A |  |  | 0 | #N/A |  | 0 | #N/A
d) Third Floor | 2026-09-21 | #N/A |  |  | 0 | #N/A |  | 0 | #N/A
Lift lobby | 2026-10-20 | 2026-12-20 | sqm | 290 | 0 | 0% | 0% | 290 | 4.7541 | 1 | 0
Interior Works | 2026-11-18 | 2026-12-18 | sqm | 530 | 0 | 0% | 0% | 530 | 17.6667 | 2 | 0
SS Handrail | 2026-11-10 | 2026-12-20 | Rm | 475 | 0 | 0% | 0% | 475 | 11.875 | 1 | 0
OT Rooms
Ground Floor ( 2 Nos.)
Civil Work | 2026-05-25 | 2026-08-28 |  |  |  | 100% | 100%
OT Works | 2026-08-28 | 2026-10-15 |  |  |  | 38% | 38% |  |  | 4 | 0
2nd Floor (2 Nos.)
Civil Work | 2026-06-20 | 2026-10-03 |  |  |  | 96% | 99% |  |  | 8 | 8
OT Works | 2026-10-03 | 2026-10-30 |  |  |  | 0% | 0%
3rd Floor (12 Nos.)
Civil Work | 2026-07-05 | 2026-10-30 |  |  |  | 25% | 31% |  |  | 10 | 12
OT Works | 2026-10-30 | 2026-12-21 |  |  |  | 0% | 0%
CSSD Room
Civil Work | 2026-07-10 | 2026-08-30 |  |  |  | 100% | 100% |  | - | -
Service Oriented Work | 2026-09-01 | 2026-11-25 |  |  |  | 54% | 58%
Above Terrace
Staircase - Head Room | 2026-09-15 | 2026-10-30 | CUM | 340 |  | 33% | 38% |  | 9.1652 | 2 | 3
Over Head Tank | 2026-09-25 | 2026-11-01 | sqm | 350 |  | 42% | 42% |  | 8.12 | 3 | 4
Terrace Waterproofing | 2026-09-07 | 2026-10-30 | sqm | 3754 |  | 68% | 68% |  | 52.2296 | 5 | 3
Truss & Polycarbonate Sheet | 2026-10-05 | 2026-10-25 | sqm | 884.5 |  | 64% | 67% |  | 16.2158 | 2 | 0
External
Elevation A | 2026-08-05 | 2026-12-10 | sqm | 935 |  | 38% | 42% |  | 8.4734 | 3 | 8
Elevation B | 2026-08-18 | 2026-12-12 | sqm | 490 |  | 14% | 14% |  | 6.3848 | 2 | 5
Elevation C | 2026-09-05 | 2026-12-18 | sqm | 564 |  | 8% | 17% |  | 6.5017 | 2 | 2
Elevation D | 2026-08-10 | 2026-12-10 | sqm | 485 |  | 17% | 25% |  | 5.6836 | 2 | 0
Fascia Beam | 2026-09-02 | 2026-11-30 | Rm | 437.6 |  | 24% | 33% |  | 5.4295 | 2 | 3
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-01-12 | 2026-09-10 | Rm | 1537 |  | 100% | 100% | 0 | 0 | 0 | 0
CI/GI Piping | 2026-01-27 | 2026-12-10 | Rm | 4560 |  | 64% | 69% | 1203 | 22.0875 | 6 | 4
Ducting & Insulation | 2026-01-20 | 2026-10-31 | sqm | 9830 |  | 98% | 98% | 76 | 8.1917 | 2 | 5
Fire Piping installation | 2026-01-10 | 2026-12-02 | Rm | 8425 |  | 69% | 71% | 1856 | 43.6295 | 11 | 8
MGPS Copper Piping | 2026-09-10 | 2026-12-18 | Rm | 8263 |  | 24% | 24% | 5672 | 87.2206 | 22 | 15
PTTS Pipe installation | 2026-10-10 | 2026-12-05 | Rm | 820 |  | 0% | 0% | 692 | 14.6429 | 4 | 3
Under deck Insulation | 2026-11-01 | 2026-12-05 | sqm | 3121 |  | 0% | 0% | 2650 | 91.7941 | 23 | 16
Second Fix
Wiring | 2026-09-03 | 2026-11-27 | Rm | 58034 |  | 18% | 25% | 16532 | 853.4412 | 27 | 18
Cable Laying & Panel Instt. | 2026-09-05 | 2026-11-21 | Rm | 23078 |  | 37% | 38% | 6532 | 317.9636 | 23 | 15
UPS Installation | 2026-12-05 | 2026-12-20 | No. | 4 |  | 0% | 0% | 0.4 | 0.26667 | 0 | 0
HVAC Pipe Testing | 2026-07-27 | 2026-12-09 | Rm |  |  | 47% | 47% | 854 | 0 | 0 | 0
AHU Connection | 2026-07-27 | 2026-12-09 | No. |  |  | 25% | 25% | 76 | 0 | 0 | 0
Wet Riser & FHC installation | [5 empty] | #N/A |  | 6 | 0 | 0
CAT 6 cabling | 2026-06-16 | 2026-12-08 | Rm | 58362 |  | 42% | 45% | 25721 | 517.7274 | 22 | 19
PA & FAS cabling | 2026-06-16 | 2026-11-27 | Rm | 25900 |  | 63% | 64% | 4381 | 182.8235 | 18 | 17
Fire Panel Installation | 2026-10-10 | 2026-10-26 | No. |  |  | 0% | 0% | 1 | 0 | 0 | 0
Network Switch | 2026-10-15 | 2026-12-11 | No. |  |  | 0% | 0% | 6 | 0 | 0 | 0
Final Fixture | 2026-11-20 | 2026-12-10 |  |  |  | 0% |  | 8
Terrace
PHE Piping installation | 2026-10-15 | 2026-11-25 | Rm |  |  | 0% |  | 1872 | 62.5 | 6 | 5
Cable Tray Installation | 2026-10-15 | 2026-11-21 | Rm |  |  | 100% |  | 0 | 0 | 0 | 0
Solar Panel Installation | 2026-11-05 | 2026-12-16 | No. |  |  | 0% |  | 195 | 5 | 1 | 0
OHT | 2026-11-05 | 2026-12-10 | No. |  |  | 41% |  | 572 | 11.6032 | 1 | 4
Terrace Waterproofing | 2026-09-10 | 2026-12-05 | sqm |  |  | 68% |  | 324 | 12.6875 | 1 | 3
Truss with Polycarbonate Sheet | 2026-09-30 | 2026-11-15 | sqm |  |  | 0% |  | 265 | 4 | 0 | 2
Lift Installation with slow speed
2 Nos. | 2026-09-30 | 2026-11-05 | No. | 2 |  | 0% | 0% |  | 6.897% | 4 | 6
1 Nos. | 2026-10-07 | 2026-11-18 | No. | 1 |  | 0% | 0% |  | 2.381% | 0
2 Nos. | 2026-10-11 | 2026-11-28 | No. | 2 |  | 0% | 0% |  | 4.167% | 0
2 Nos. | 2026-11-15 | 2026-12-21 | No. | 2 |  | 0% | 0% |  | 5.556% | 0
2 Nos. | 2026-10-24 | 2026-12-08 | No. | 2 |  | 0% | 0% |  | 4.444% | 0
2 Nos. (Dumb waiter) | 2026-10-28 | 2026-12-17 | No. | 2 |  | 0% | 0% |  | 4% | 0
Permanent Power
ESS1 to EMR Cable laying | 2026-09-10 | 2026-10-08
Main LT Panel Energisation | 2026-10-25 | 2026-11-10
Rising Main | 2026-10-28 | 2026-11-15
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
Formulas:
Asking Rate = (1-[Achieved as on 3-Oct])*[SCOPE]/([Target Date]-(IF([PLAN / ACTUAL START]>TODAY(),[PLAN / ACTUAL START],TODAY())))
Target Date = VLOOKUP([ACTIVITY],[2]EMR!$B7:D131,3,FALSE)
Target Date = [PLAN / ACTUAL START]+45
PLAN / ACTUAL START = [PLAN / ACTUAL START, row above]+25